SMS PLATFORM

End-to-End Architecture

and Phased Delivery Plan

Campaign through Delivery — services, scaling, stop control, and sequencing

The one decision that shapes everything else Two of the stated requirements pull against each other: run everything on Kafka messages, and stop mid-campaign so that if 500 of 1000 have gone the remaining 500 do not. They can both be met — but only if Kafka carries SIGNALS and the database carries the WORK QUEUE. Section 3 sets out why, and what the alternative costs.

# Contents

# 1. What Has Been Asked For

Restated so we are working from the same list.

| Requirement | Interpretation |
| --- | --- |
| Everything driven by Kafka messages | Services are triggered by events rather than polling blindly, and are decoupled from one another. |
| Stop mid-campaign from the UI | If 1000 are queued and 500 have gone, clicking stop prevents the remaining 500. |
| Run any service on multiple servers | Instances can be added or removed freely with no coordination between them and no conflict. |
| Build campaign through delivery | The whole pipeline, not one piece of it. |
| New tables, procedures, EF as needed | Free to design the data layer rather than fit an existing one. |
| Four to six projects | Separate deployable services rather than one application. |
| APIs over the services | A REST surface the Razor UI and other callers can use. |
| Phased, take the time to do it properly | Correctness over speed. |

Two things are being reused rather than rebuilt: the EOS and RM account-fetch logic, which comes from Santosh, and the existing CampaignManager projects as reference.

# 2. Where The Requirements Conflict

Everything on the list is achievable. Two items interact in a way that decides the whole design, so it is worth being explicit about before code exists.

### The interaction

Suppose campaign publishes 1000 message identifiers onto a Kafka topic. Delivery consumes them and sends. After 500, an operator clicks stop.

The remaining 500 identifiers are already in the partition. They cannot be withdrawn — a published Kafka message cannot be unpublished. Delivery will read them, because that is what a consumer does.

So to honour the stop, delivery must consult something OTHER than the message before each send. In practice that means a database read. Which means Kafka did not deliver the stop capability; the database did.

The consequence worth noticing If Kafka carries the work items, a mid-campaign stop still requires a database check on the send path. The message queue adds no help there, while adding the problems of replay and rebalance. If Kafka carries signals and the database carries the queue, the stop is a single status update and the next claim simply returns nothing.

# 3. Recommended Shape: Kafka Signals, Database Queue

Kafka does real and valuable work here — it just should not be the queue.

## 3.1 How it works

Campaign service writes 1000 rows to SMS_Queue_Detail (Status = Init) publishes ONE message: "run 4821 has work" Compliance service (N instances) woken by the Kafka signal claims a batch atomically WHERE Status = Init AND run is still Running evaluates, writes decisions publishes "run 4821 approved" Delivery service (N instances) woken by the Kafka signal claims a batch atomically WHERE Status = Eligible AND run is still Running sends, records outcome

Kafka carries the fact that work exists. The database carries the work and its state. Each service is woken immediately rather than discovering work on its next poll, which is the benefit that was actually wanted from messaging.

## 3.2 What this gives, requirement by requirement

| Requirement | How it is met |
| --- | --- |
| Event driven | Every service is triggered by a Kafka signal. Nothing polls blindly waiting for work. |
| Mid-campaign stop | One update to the run's status. The next claim query returns zero rows because the claim filters on it. No message needs withdrawing. |
| Multiple servers | The atomic claim hands each instance a disjoint batch. No leader election, no partition assignment, no shared state between instances. |
| No dependencies between instances | Instances never talk to each other. They coordinate only through the row-level lock the database already provides. |

## 3.3 The claim, which is the mechanism everything rests on

UPDATE TOP (@batch) d WITH (READPAST, ROWLOCK, UPDLOCK) SET d.SMSStatus = @claimed, d.ClaimedBy = @instanceId, d.ClaimedUtc = SYSUTCDATETIME() OUTPUT inserted.ID, inserted.Mobile, inserted.MessageText FROM dbo.SMS_Queue_Detail d JOIN dbo.SMS_Queue_Mst m ON m.ID = d.SMSQueue_Mst_ID WHERE d.SMSStatus = @ready AND m.Status = @running; -- the stop switch

Two properties matter here. READPAST makes a second instance skip rows the first has locked rather than queue behind them, so instances never block one another. And the join to the run's status means stopping a run stops every instance at once, without any of them being told.

## 3.4 If the decision goes the other way

Kafka as the work queue is a legitimate design and worth stating fairly. What it costs here:

- Mid-campaign stop still needs a database check per message on the send path, so nothing is saved.

- Consumer rebalance reprocesses in-flight messages, so duplicate sends become routine rather than exceptional — which requires the idempotency key regardless.

- Parallelism is capped by partition count rather than being freely adjustable.

- A stopped campaign leaves messages sitting in partitions. On restart they replay, and without dedupe some send twice.

None of these are fatal. They are simply costs paid for no corresponding benefit, given what has been asked for.

# 4. What Stop Actually Guarantees

Worth being precise, because “stop” can mean three different things and only two are achievable.

| Meaning | Achievable | Detail |
| --- | --- | --- |
| Take no further work | Yes, immediately | The next claim returns nothing. This is the switch. |
| Halt the batch already claimed | Yes, but not instantly | Bounded by batch size. See below. |
| Recall messages already sent | No | Once a message is with the provider it is gone. No design changes this. |

### The overshoot, stated honestly

A batch already claimed runs to completion. Abandoning it mid-way would strand rows in a claimed state with nothing to reclaim them, requiring manual repair — worse than finishing.

So the worst-case overshoot after clicking stop is one batch per running instance. That is a number the operator controls:

batch 500, 1 instance -> up to 500 more may send batch 100, 3 instances -> up to 300 more may send batch 25, 3 instances -> up to 75 more may send

Design implication Batch size is the dial that trades throughput against stop precision, and it belongs in the UI rather than in configuration files. For a campaign where stopping precisely matters, an operator can lower the batch before starting. For a large overnight run they can raise it. Same code, different setting. A claim-timeout reaper is also needed: if an instance dies holding a batch, those rows must return to the queue after a timeout rather than sitting claimed forever.

# 5. Running On Multiple Servers

The requirement was that any service can run on several servers with no dependencies between them. The claim mechanism gives this, with three caveats worth designing for now rather than discovering later.

## 5.1 What works without any further thought

- Add or remove instances at any time. No registration, no configuration change, no restart of the others.

- No leader election and no distributed lock. Coordination is the row lock the database already provides.

- An instance dying loses only the batch it held, which the reaper returns to the queue.

## 5.2 Three things that do not scale automatically

### Provider rate limits multiply

If delivery is limited to 20 messages per second and three instances run, the provider sees 60. A per-instance limit is not a global limit.

Two options: divide the limit across the expected instance count and accept the waste, or hold the limit centrally. Dividing is simpler and adequate at low instance counts; a shared counter becomes worth it later.

### Per-recipient and per-campaign counting must be read fresh

Two instances evaluating messages to the same recipient at the same moment can each read a count of two against a limit of three, and both proceed — putting the recipient at four. The count has to be read inside the same operation that claims, or enforced by a constraint, not read separately and trusted.

### Cached lookups drift per instance

The zip and state tables are cached in memory for good reason. But each instance caches independently, so a rule change reaches instances at different times. Acceptable for data that changes twice a year, worth knowing when someone updates a rule and sees inconsistent behaviour for a few minutes.

## 5.3 Where the control API must not live

A design point that is easy to get wrong Do not expose start and stop as HTTP endpoints on the worker services. With three delivery instances running, which one does the UI call? Calling one stops one. The UI would need to discover and call all of them, and would be wrong the moment an instance is added. Control belongs in the database, written by a separate API and read by every instance. Then stop works identically for one instance or twenty, and the UI does not need to know how many exist.

# 6. Project Structure

Six projects. Four are deployable, two are libraries.

| Project | Type | Responsibility |
| --- | --- | --- |
| Sms.Core | Library | Domain logic: compliance decisions, time zone resolution, phone normalisation, segment counting, message contracts. No I/O, fully unit-testable. |
| Sms.Data | Library | EF Core context, entities, repositories, and the atomic claim. The only project that knows SQL. |
| Sms.Campaign.Service | Worker | Expands a campaign into queue rows using the EOS and RM account logic, builds message text, signals compliance. |
| Sms.Compliance.Service | Worker | Evaluates each message against state rules, consent, suppression, caps and the local send window. Includes scheduling, since holding a deferred message is part of the same decision. |
| Sms.Delivery.Service | Worker | Sends via Webex, records the provider response, applies retry policy. |
| Sms.Api | Web API | Control endpoints for the UI, campaign and run management, monitoring queries, and the Webex webhook receiver. |

## 6.1 Why compliance and scheduling are one service

They were separated in an earlier discussion and then merged, correctly. If compliance decides a message is legal and a separate scheduler releases it later, a queue delay can push the release outside the window that was checked. The check passes and the send is still non-compliant.

Deciding and releasing in the same service means the decision is re-verified at release. One less way to be wrong.

## 6.2 Why the webhook receiver sits in Sms.Api

It is an HTTP endpoint and Sms.Api is the only project already hosting HTTP. A separate service purely to receive callbacks would add a deployment for one controller.

## 6.3 Relationship to the existing projects

Sms.Core and Sms.Data reference CampaignManager.Models and CampaignManager.DTO for shared entities and view models, as directed. They do not reference CampaignManager.Services — the SMS pipeline should not depend on the voice campaign implementation, or a change there breaks SMS for reasons nobody expects.

# 7. Data Model Additions

Building on the tables that already exist rather than replacing them.

## 7.1 Changes to SMS_Queue_Detail

| Column | Purpose |
| --- | --- |
| IdempotencyKey CHAR(64), UNIQUE | Prevents the same logical message existing twice. The single most important addition — see 7.4. |
| ProviderMessageId NVARCHAR(128) | Webex transid. Delivery receipts key on it; without it a receipt cannot be matched to its message. |
| NextAttemptUtc DATETIME2 | When a deferred or retrying message becomes eligible again. |
| ClaimedBy VARCHAR(100) | Which instance holds this row. Needed for the reaper and for diagnosing a stuck batch. |
| ClaimedUtc DATETIME2 | When it was claimed, so the reaper can find abandoned rows. |
| AttemptCount INT | Retry counting, and the ceiling that stops infinite retries. |

## 7.2 New SMSStatus values

The existing set runs Init, BLOCK, Eligible, Queued, Sent, Delivered, Failed. Three gaps:

| Value | Name | Why it is needed |
| --- | --- | --- |
| 7 | Deferred | Compliance said not yet. The Time_Range rule action is QUEUE, so this outcome is expected, but currently has nowhere to sit. Leaving it at Init means rescanning the whole backlog every cycle. |
| 8 | Claimed | An instance holds this row and is working on it. Distinguishes in-flight from available, which is what makes the claim safe. |
| 9 | DeadLetter | Retries exhausted. Terminal, and separated from Failed so a permanent giving-up is distinguishable from a single failed attempt. |

## 7.3 New tables

| Table | Purpose |
| --- | --- |
| Sms_Service_Control | One row per service. Enabled flag, poll interval, batch size, heartbeat. This is what the UI writes to stop a service or change its pacing. |
| State_TimeZone_Default | Fallback zone for the states that lie in a single time zone, used when a zip does not resolve. |
| Sms_Delivery_Attempt | One row per send attempt, not per message. A message retried four times has four rows. Needed to answer why something failed rather than only that it did. |

## 7.4 The idempotency key, and why it comes first

Without a unique key identifying a logical message, the same recipient can receive the same message twice through several ordinary routes: a retry after an unrecorded success, a re-run of a partially failed generation, or a consumer rebalance if messaging carries work items.

The key is a hash of run, account, template version and normalised phone, with a UNIQUE constraint. Creating the same logical message twice then fails at the database rather than becoming a second text.

Why this is the first thing to build It is one column and one index while the table is small. After go-live it is a migration against millions of rows, plus whatever went out in the meantime. It also carries direct regulatory weight. State_TCPA_Rules sets Florida at one message per thirty days. A single duplicate there is not an annoyance; it is a breach of the strictest rule in the table.

## 7.5 EF Core or stored procedures

Both, split by what each is good at.

| Use | For | Because |
| --- | --- | --- |
| Stored procedures | Account selection for EOS and RM; the atomic claim | Account selection is complex cross-system SQL that already exists in Santosh's code. The claim needs table hints EF cannot express. |
| EF Core | Everything else | Readable, testable, and the queries are straightforward. |

# 8. API Surface

Sms.Api serves the Razor UI and any other caller. Grouped by what it is for.

| Area | Endpoints |
| --- | --- |
| Campaign | create, update, list, get; validate before running |
| Run control | start a run; stop a run; resume; get progress |
| Service control | list services with health; stop or start a service; change interval and batch size |
| Monitoring | queue counts by status; block reasons grouped; failure reasons grouped; per-run progress |
| Message inspection | find a message by account or mobile; full decision history for one message |
| Suppression | search; add; remove; bulk import |
| Webhooks | Webex delivery receipt; Webex inbound message |

### Two endpoints worth designing carefully

Stop a run. Must be idempotent — clicking twice is not an error — and must return immediately rather than waiting for instances to notice. It writes a status; the instances discover it on their next claim.

Message inspection. When someone asks why a specific person did not receive a message, this is the answer. It needs the decision, the reason, the resolved time zone, the state rule applied and every attempt. Without it that question requires a developer and a query window.

# 9. Phased Plan

Ordered so that each phase is independently useful and the expensive-to-change decisions come first.

## P0   Foundations

Nothing here is visible, and everything later depends on it. Cheapest now, most expensive to retrofit.

- Schema changes from section 7 — idempotency key, provider message id, claim columns, new status values.

- Sms.Core and Sms.Data projects, with the compliance logic that already exists moved in.

- Shared Kafka message contracts.

- Sms_Service_Control table and the reader that honours it.

- State_TimeZone_Default seeded; real zip data loaded.

- Prove the atomic claim under concurrency — run three instances against one table and confirm no row is claimed twice.

Done when: three instances can claim from the same table concurrently without overlap, and the unique key rejects a duplicate insert.

## P1   Campaign service

Produces the work everything else consumes. Nothing downstream can be tested without it.

- EOS and RM account selection, using Santosh's existing code.

- Message construction from the template, with the double-brace merge fields.

- Queue row creation with the idempotency key populated.

- Kafka signal on completion.

- Run status honoured, so a stop takes effect.

Done when: a campaign produces correct queue rows and stopping it mid-generation halts cleanly.

## P2   Compliance service

Largely written already. The regulatory exposure sits here.

- Bind to ZipCode_TimeZones and State_TCPA_Rules.

- Apply the decision order: state rule, consent, suppression, recipient cap, campaign cap, window.

- Persist deferred times so a restart loses nothing.

- Wire consent, or record explicitly that written-consent states are excluded for now.

- Settle whether zone resolution lives in the procedure or in code — one place, not both.

Done when: a mixed-state batch produces correct allow, defer and block decisions with reasons on every row.

## P3   Delivery service

The send path is already proven manually. What is missing is everything around it.

- Webex call using the confirmed flow trigger contract.

- Provider message id recorded against the row.

- Retry policy with a ceiling and a dead-letter state.

- Per-client sender numbers, replacing the hardcoded one.

- Rate limiting, with the multi-instance caveat from 5.2 addressed.

Done when: messages send, outcomes are recorded, and a provider outage produces retries rather than losses.

## P4   Status and inbound

Closes the loop. Until this exists, delivery rate is not measurable.

- Notify URL configured on the Connect flow so receipts arrive at all.

- Webhook receiver, authenticated, and safe to receive the same callback twice.

- Inbound STOP handling with immediate suppression across all campaigns.

- Confirm whether Webex forwards inbound replies to us; if not, an inbound flow is needed.

Done when: a sent message reaches Delivered or Failed without manual intervention.

## P5   API and UI

Hard to operate what cannot be seen, and this is where problems surface first.

- Control endpoints for run and service management.

- Monitoring views: progress, block reasons, failure reasons.

- Message inspection — why did this person not receive this.

- Suppression management.

- Razor screens over the above.

Done when: an operator can start, stop, monitor and explain a campaign without a developer.

## P6   Hardening

The difference between working and dependable.

- Claim-timeout reaper for instances that die holding a batch.

- Alerting on queue depth, stalled runs and dead heartbeats.

- Segment count shown at template design time.

- Dry run: what would be sent, without sending it.

- Load test at realistic volume.

Done when: the system survives an instance dying, a provider outage and a full-volume day.

# 10. What Is Needed From Others

These block specific phases rather than the plan as a whole.

| Needed | From | Blocks |
| --- | --- | --- |
| EOS and RM account-fetch code | Santosh | P1 |
| Whether the queue moves to a separate database | Architecture decision | P0 — affects every connection and any cross-database join |
| Where consent lives, and whether it distinguishes express from written | Business or data owner | P2 — written-consent states cannot be sent to without it |
| Notify URL set on the Connect flow | Whoever owns Webex configuration | P4 entirely |
| Whether Connect deduplicates on Correlation ID | A five-minute test against Webex | P3 retry design |
| Real zip to time zone data | Purchase or download | P2 — the table currently holds about seven rows |
| Whether inbound STOP is forwarded to us | Webex configuration | P4 |

## 10.1 A note on the Correlation ID test

The Webex SMS node has an unused Correlation ID field. Sending the same value twice and counting the messages received answers whether the provider deduplicates. If it does, passing our idempotency key closes the last duplicate-send window — the case where we sent successfully but never learned that we did, which our own database key cannot cover. Five minutes of work for a genuinely material answer.

# 11. Risks

| Risk | Consequence | Mitigation |
| --- | --- | --- |
| Duplicate sends | Regulatory breach, particularly in Florida where the limit is one per thirty days | Idempotency key in P0. Provider-side key if Connect supports it. |
| Sending outside legal hours | Regulatory breach | Zone resolution through real time zone data with daylight saving handled; block rather than guess when unresolved. |
| Instance dies holding a batch | Rows stuck, campaign appears stalled | Claim-timeout reaper in P6. Consider bringing forward if instance counts rise early. |
| Provider rate limit exceeded | Throttling or suspension | Per-instance limits divided, or a shared counter. Decide before running multiple delivery instances. |
| Cost overrun from message length | Silent doubling of spend | Segment count at template design time, accounting for the text the Connect flow appends. |
| Two implementations of one rule | Silent divergence | Zone resolution in one place only. Applies to any rule expressible in both SQL and code. |

If one thing is taken from this document Settle the Kafka question first, because everything else follows from it. Signals plus a database queue meets every requirement on the list, including the mid-campaign stop, and needs no mechanism that does not already exist. Then build P0 before anything visible. The idempotency key in particular is one column today and a migration under load later.